## Risk_Assessement
Description	Evaluation	Probability	Impact level	Responsibility	Response	Control Measures

Underlying code does not work	The code is broken or some parts work only	Low	High	Coder - Attila	Revert to most recent stable version	Tests always have to be carried out
Code testing does not work	The code testing is not ready or not working	Medium	Medium	Coder - Attila	Has to be fixed or finalized asap	Writing the test immediately after the code
Problems with pipeline	Automated updateing, testing does not work	Low	High	DevOps - Attila	Separating the elements to find the faulty part and fix it	Step by step tested building of the pipeline
Virtual machines go down	Application goes offline	Low	High	DevOps - Attila	Checking on the vm and contacting service provider	Redundant design by virtualization tools
Front end design is not adequate	Webpage design does not reflect client's need	Medium	Low	Project Manager	Talking to the client, reevaluate ideas	Need accurate details of the customer's need
Cyber security is not adequete	Some parts of the code, webpage or the pipeline are exposed	Low	Medium	Coder - Attila	White hacking test	Cybersecurity plan has to be done
Deadlines are not met	Not meeting the deadlines	Medium	Medium	DevOps - Attila	Assigning new deadlines syncronised with plan	Deadlines has to be clear and realistic